## Bug Report
AUTOMATION TEST STORE — DEFECT / BUG REPORT
Source: Manual Test Execution — AUTOMATION_STORE_TEST_CASES_EXECUTION.xlsx ¦ Environment: Demo Web Store
Bug ID | Module | Test Case ID | Bug Summary | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity | Priority | Status | Notes
BUG-001 | Registration | Rg_10 | Telephone field accepts non-numeric input without validation | 1. Navigate to Registration page. 2. Enter non-numeric characters in Telephone field. 3. Fill other fields. 4. Click 'Continue'. | Telephone: 'ABCDE' | Appropriate error message for invalid phone format is displayed. | Form submitted without showing phone format validation error. | Medium | Medium | Open | Data-integrity risk; invalid phone numbers stored in DB.
BUG-002 | Registration | Rg_16 | Password visibility toggle (eye icon) missing on Registration page | 1. Type password in Password field. 2. Click Eye/Show icon. | Password text | Password characters switch between masked dots and plain text. | Password toggle icon not present on registration page. | Low | Low | Open | Usability enhancement, no functional blocker.
BUG-003 | Authentication | Login_06 | No account lockout after multiple consecutive failed login attempts | 1. Attempt login with invalid password 5 consecutive times. | valid_username, wrong_password | Account is temporarily locked with warning message displayed. | No account lockout triggered after 5 failed login attempts. | High | High | Open | Security concern — exposes accounts to brute-force attacks.
BUG-004 | Authentication | Login_08 | 'Remember Me' checkbox not available on Login form | 1. Enter valid credentials. 2. Check 'Remember Me'. 3. Click 'Login'. 4. Close and re-open browser. | Valid credentials | User remains logged in without re-entering credentials. | 'Remember Me' option not available on login form. | Medium | Medium | Open | Feature appears to be missing from UI entirely.
BUG-005 | Authentication | Login_11 | Cached account page briefly renders after Logout via browser Back button | 1. Log out from account. 2. Click browser's 'Back' button. | Post-logout state | User cannot access protected account pages without re-logging in. | Cached account page renders briefly before redirecting to login page. | High | High | Open | Potential session/cache security issue; sensitive data briefly exposed.
BUG-006 | Search | Search_09 | Auto-complete search suggestions not implemented | 1. Type first 3 letters of product name. | 'Tot' | Dropdown overlay shows matching live auto-suggestions. | Auto-complete suggestion dropdown not implemented on search bar. | Low | Low | Open | Enhancement — not a blocking defect.
BUG-007 | Search | Search_19 | 'Clear' (X) button missing inside search bar | 1. Type text in search bar. 2. Click 'X' clear button. | Sample text | Search input field is instantly cleared. | 'X' clear button not available inside search bar. | Low | Low | Open | Minor usability gap.
BUG-008 | Cart | Cart_05 | Out-of-stock product can be added to cart without warning | 1. Navigate to out-of-stock product page. 2. Check 'Add to Cart' availability. | Out of stock item | 'Add to Cart' button is disabled or error alert is shown. | Out of stock item allowed addition to cart without warning. | High | High | Open | Can lead to unfulfillable orders.
BUG-009 | Cart | Cart_16 | No dedicated 'Clear Cart' option available | 1. Add multiple items to cart. 2. Click 'Clear Cart' button (if available). | Multiple cart items | All items are cleared and cart status becomes empty. | No dedicated 'Clear Cart' button found; user must remove items individually. | Low | Low | Open | Usability enhancement.
BUG-010 | Checkout | Checkout_12 | Checkout completes even when item stock is zeroed out concurrently | 1. Hold product in checkout. 2. Simulate item going out of stock in backend. 3. Click 'Confirm Order'. | Out-of-stock trigger | Error alert indicates item stock is no longer available. | System allowed checkout completion despite item stock zeroing out. | Critical | High | Open | Overselling risk — direct business/financial impact.
BUG-011 | Checkout | Checkout_18 | Invalid ZIP/postal code format accepted at Checkout | 1. Enter invalid ZIP code format for selected country. 2. Click 'Continue'. | ZIP: 'ABC!!' | Validation error regarding incorrect postal code format is shown. | Invalid ZIP code accepted without format validation error. | Medium | Medium | Open | May cause downstream shipping/tax calculation errors.
BUG-012 | User Interface | UI_14 | Newsletter subscription popup modal does not display for new visitors | 1. Access homepage as new visitor. | First-time session | Promotional newsletter subscription modal displays over content. | No newsletter popup modal appeared on initial homepage visit. | Low | Low | Open | Marketing feature gap; no functional impact.
BUG-013 | User Interface | UI_15 | Language switcher does not translate UI text | 1. Locate header language dropdown. 2. Switch language (e.g. English to Spanish). | Language toggle | UI text labels translate according to selected language. | Language dropdown options failed to update UI text strings. | Medium | Medium | Open | Localization feature not functioning.
BUG-014 | User Interface | UI_16 | Dark / Light mode theme toggle not present in application | 1. Click theme toggle icon in header/footer. | Theme switch icon | Color scheme transforms seamlessly between Dark and Light mode. | Dark/Light mode feature not present on application UI. | N/A | Low | Blocked | Feature not implemented; test case blocked, not a defect against existing functionality.

## Summary
DEFECT SUMMARY
Total Defects Logged | 14
By Severity
Critical | 1
High | 3
Medium | 4
Low | 5
N/A | 1
By Status
Open | 13
Blocked | 1
Closed | 0
By Module
Registration | 2
Authentication | 3
Search | 2
Cart | 2
Checkout | 2
User Interface | 3